## Start Here
Basement Finishing Budget & Project Tracker
From BasementCalculator.com · 2026 pricing · Works in Excel and Google Sheets
Your project at a glance
| Calculator estimate |  | Working budget | Spent to date
| 33271.5235 |  | 33271.5235 | 0
| Forecast final cost |  | Over / under budget | Cost per sq ft
| 33271.5235 |  | 0 | 41.5894
How to use this workbook
| 1. Project Setup | Enter your basement size, finishes and extras. The estimate uses the same prices as our online calculator.
| 2. Budget | Review the line-by-line estimate. Type your own number in the yellow "Your budget" column for any line.
| 3. Quotes | Log every contractor quote. Mark the one you hire "Selected = Yes" and it flows into your budget.
| 4. Expenses | Record every payment as you go. Spending updates your budget and forecast automatically.
| 5. Schedule | Follow the 12 steps in order and track inspections so nothing gets covered up too early.
Color key
| Yellow cell | Yours to fill in or change.
| White or gray cell | Calculated automatically. No need to edit.
Next steps
Get up to 3 free quotes from local basement pros →
Shop materials at Lowe's →
Compare financing: HELOC vs. home equity vs. personal loan →
All free basement calculators →
Estimates are for planning only and use national average 2026 pricing. Get at least three written quotes before you start. Some links are affiliate links: we may earn a commission at no extra cost to you. basementcalculator.com/affiliate-disclosure

## Project Setup
Project Setup
Fill in the yellow cells. The Budget tab builds a line-by-line estimate from these, using the same prices as the calculator on basementcalculator.com.
Project
| Project name | My basement finish
Address
Planned start date
Target finish date
Your basement
| Area to finish (sq ft) | 800 | Leave out a furnace or utility room that stays unfinished.
| Ceiling height (ft) | 8 | Most codes want about 7 ft of finished height.
| Rooms to wall off | 1 | Bedrooms, office, gym, storage. Open rec space doesn't count.
| Where you live | Average U.S. costs | Lower-cost = rural, much of the South and Midwest. Very high = NYC, Boston, SF Bay Area.
Finishes
| Overall quality | Mid-range
| Flooring | Luxury vinyl plank | Waterproof LVP is the go-to below grade.
| Walls | Drywall
| Ceiling | Drywall | A drop ceiling takes 3–6 inches of headroom.
| Wall insulation | Fiberglass batts
Bathroom and extras
| Bathroom | None
| Plumbing rough-in already in the floor? | Yes | "No" adds $3,000–$6,000 to cut the slab for drains.
| Heating & cooling extension | Yes
| Insulated subfloor | No
| Interior waterproofing | No
| Egress window | No | Required for a legal bedroom.
| Wet bar | No
| Media room prewire | No
| Soundproofed ceiling | No
| Permits & inspections | Yes | Required almost everywhere.
| Contingency buffer | 10% | Money set aside for surprises. Pros recommend 10–15%.
Who does the work
Set any trade to DIY to remove its labor (adds a $150 tool allowance).
| Prep & demo | Pro
| Framing | Pro
| Insulation | Pro
| Electrical | Pro | Permit + inspection usually required.
| Plumbing | Pro | Often must be licensed.
| Drywall & ceiling | Pro
| Flooring | Pro
| Painting | Pro
| Trim & doors | Pro
Calculated from your inputs
| Estimated wall perimeter (ft) | 130.1076 | Based on the floor area, assuming a roughly square basement.
| Exterior wall area (sq ft) | 1040.8612
| Partition walls (linear ft) | 24 | About 24 ft of new wall per room.
| Partition wall area, both sides (sq ft) | 384
| Region materials factor | 1
| Region labor factor | 1
| Region base permit cost | 1200
| Quality materials factor | 1
| Quality labor factor | 1

## Budget
Budget
Estimate vs. your budget, quotes and spending. Yellow cells are yours to fill in; everything else updates automatically.
Calculator estimate |  | Working budget |  | Selected quotes |  | Spent to date |  | Forecast final cost |  | Over / under
33271.5235 |  | 33271.5235 |  | 0 |  | 0 |  | 33271.5235 |  | 0
Nothing spent yet. | [7 empty] | Need quotes? Get up to 3 free quotes from local pros →
Category | Trade | Included? | Est. materials | Est. labor | Estimate | Your budget (optional) | Working budget | Selected quote | Spent to date | Forecast final | Remaining to spend | Over / under budget | Price it online
Prep, cleanup & dumpster | Prep & demo | Yes | 320 | 880 | 1200 |  | 1200 | 0 | 0 | 1200 | 1200 | 0
Framing & doors | Framing | Yes | 1808.9688 | 2503.5071 | 4312.4759 |  | 4312.4759 | 0 | 0 | 4312.4759 | 4312.4759 | 0 | Framing calculator + lumber list
Insulation | Insulation | Yes | 936.7751 | 832.6889 | 1769.464 |  | 1769.464 | 0 | 0 | 1769.464 | 1769.464 | 0 | Foam vs. fiberglass guide
Walls | Drywall & ceiling | Yes | 1068.6459 | 3205.9377 | 4274.5835 |  | 4274.5835 | 0 | 0 | 4274.5835 | 4274.5835 | 0
Ceiling | Drywall & ceiling | Yes | 640 | 1760 | 2400 |  | 2400 | 0 | 0 | 2400 | 2400 | 0 | Basement ceiling options
Electrical & lighting | Electrical | Yes | 1280 | 2560 | 3840 |  | 3840 | 0 | 0 | 3840 | 3840 | 0
Bathroom | Plumbing | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Bathroom cost calculator
Flooring | Flooring | Yes | 2560 | 1440 | 4000 |  | 4000 | 0 | 0 | 4000 | 4000 | 0 | Basement flooring guide
Paint & finishing | Painting | Yes | 778.7014 | 2781.0765 | 3559.7779 |  | 3559.7779 | 0 | 0 | 3559.7779 | 3559.7779 | 0
Trim & baseboard | Trim & doors | Yes | 320.5938 | 569.9445 | 890.5382 |  | 890.5382 | 0 | 0 | 890.5382 | 890.5382 | 0
HVAC extension | — | Yes | 960 | 1840 | 2800 |  | 2800 | 0 | 0 | 2800 | 2800 | 0
Insulated subfloor | Flooring | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Heated floor calculator
Interior waterproofing | — | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Waterproofing calculator
Egress window | — | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Egress window calculator
Wet bar | Plumbing | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Media room prewire | Electrical | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Home theater on a budget
Soundproofed ceiling | Drywall & ceiling | No | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Soundproofing guide
Permits & inspections | — | Yes |  |  | 1200 |  | 1200 | 0 | 0 | 1200 | 1200 | 0
Radon mitigation | — | Optional |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Radon mitigation calculator
Stairs & railings | — | Optional |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Furniture & decor | — | Optional |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Other | — | Optional |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Subtotal |  |  | 10673.685 | 18373.1546 | 30246.8396 |  | 30246.8396 | 0 | 0 | 30246.8396 | 30246.8396 | 0
Contingency | 10% |  |  |  | 3024.684 |  | 3024.684 |  | 0 | 3024.684 | 3024.684 | 0
TOTAL |  |  | 10673.685 | 18373.1546 | 33271.5235 |  | 33271.5235 | 0 | 0 | 33271.5235 | 33271.5235 | 0

## Quotes
Quotes
Log every quote you get. Mark the one you hire as Selected = Yes and it flows into your Budget. Get at least three per trade.
Get up to 3 free quotes from local basement pros → |  |  |  |  | Ask each contractor for a written, itemized quote with the same scope, so you can compare apples to apples.
Example (not counted):
Framing & doors | Example Builders LLC | Sam Lee | (555) 010-2030 | sam@example.com | 2026-10-12 | 4200 | Framing, 3 doors, soffits; materials included | Yes | Yes | 2026-11-02 | No | Valid 30 days
Quote comparison
Category | Company | Contact name | Phone | Email | Date received | Quote amount | What's included | Licensed & insured? | Reviews checked? | Earliest start | Selected? | Notes | Category | # quotes | Lowest | Highest | Selected
[13 empty] | Prep, cleanup & dumpster | 0 | 0 | 0 | 0
[13 empty] | Framing & doors | 0 | 0 | 0 | 0
[13 empty] | Insulation | 0 | 0 | 0 | 0
[13 empty] | Walls | 0 | 0 | 0 | 0
[13 empty] | Ceiling | 0 | 0 | 0 | 0
[13 empty] | Electrical & lighting | 0 | 0 | 0 | 0
[13 empty] | Bathroom | 0 | 0 | 0 | 0
[13 empty] | Flooring | 0 | 0 | 0 | 0
[13 empty] | Paint & finishing | 0 | 0 | 0 | 0
[13 empty] | Trim & baseboard | 0 | 0 | 0 | 0
[13 empty] | HVAC extension | 0 | 0 | 0 | 0
[13 empty] | Insulated subfloor | 0 | 0 | 0 | 0
[13 empty] | Interior waterproofing | 0 | 0 | 0 | 0
[13 empty] | Egress window | 0 | 0 | 0 | 0
[13 empty] | Wet bar | 0 | 0 | 0 | 0
[13 empty] | Media room prewire | 0 | 0 | 0 | 0
[13 empty] | Soundproofed ceiling | 0 | 0 | 0 | 0
[13 empty] | Permits & inspections | 0 | 0 | 0 | 0
[13 empty] | Radon mitigation | 0 | 0 | 0 | 0
[13 empty] | Stairs & railings | 0 | 0 | 0 | 0
[13 empty] | Furniture & decor | 0 | 0 | 0 | 0
[13 empty] | Other | 0 | 0 | 0 | 0
[13 empty] | Contingency | 0 | 0 | 0 | 0
Amber = fewer than 3 quotes so far.

## Expenses
Expenses
Record every payment: deposits, materials, rentals, permits. Spending flows into the Budget tab by category.
Total spent |  | Materials | Labor | Deposit | Permit | Tools & rental | Other
0 |  | 0 | 0 | 0 | 0 | 0 | 0
Buying materials yourself? Shop at Lowe's →
Example (not counted):
2026-11-04 | Framing & doors | Lowe's | 182 2x4 studs, PT plates, fasteners | Materials | 1457 | Card | Yes | Pickup order
Date | Category | Paid to | Description | Type | Amount | Payment method | Receipt saved? | Notes

## Schedule
Schedule
The 12 steps in the order builders follow. Track dates, inspections and status. Don't insulate or drywall until the rough-in inspection passes.
# | Step | Who (Pro/DIY) | Planned start | Planned finish | Done on | Status | Inspection? | Inspection date | Passed? | Notes | Helpful link
1 | Plan, budget and pull permits |  |  |  |  | Not started | No |  |  |  | Compare financing options
2 | Fix moisture problems first |  |  |  |  | Not started | No |  |  |  | Size a dehumidifier
3 | Prep the space and test for radon |  |  |  |  | Not started | No |  |  |  | Get a radon test kit
4 | Framing |  |  |  |  | Not started | Yes |  |  | Framing inspection | Framing calculator + lumber list
5 | Rough-in electrical, plumbing and HVAC |  |  |  |  | Not started | No |  |  |  | Get quotes from licensed trades
6 | Pass the rough-in inspection |  |  |  |  | Not started | Yes |  |  | Rough-in inspection | What inspectors check
7 | Insulation |  |  |  |  | Not started | No |  |  |  | Foam vs. fiberglass
8 | Drywall: ceiling first, then walls |  |  |  |  | Not started | No |  |  |  | Get drywall quotes
9 | Prime and paint |  |  |  |  | Not started | No
10 | Flooring |  |  |  |  | Not started | No |  |  |  | Basement flooring guide
11 | Trim, doors and fixtures |  |  |  |  | Not started | No |  |  |  | Shop trim and doors at Lowe's
12 | Final inspection, then move in |  |  |  |  | Not started | Yes |  |  | Final inspection
Progress
| Steps done | 0 of 12
| Blocked | 0

## Price Data
Price Data
2026 national average prices used by the BasementCalculator.com finishing calculator. Edit only if you have better local numbers.
Region adjustments
Where you live | Materials × | Labor × | Base permit $
Lower-cost area | 0.97 | 0.85 | 600
Average U.S. costs | 1 | 1 | 1200
Higher-cost metro | 1.05 | 1.22 | 2200
Very high-cost metro | 1.1 | 1.45 | 3200
Finish quality
Quality | Materials × | Labor ×
Budget | 0.8 | 0.95
Mid-range | 1 | 1
High-end | 1.45 | 1.2
Flooring ($ per sq ft of floor)
Flooring | Materials | Labor
Luxury vinyl plank | 3.2 | 1.8
Carpet + pad | 2.5 | 1.2
Laminate | 2.4 | 1.8
Engineered hardwood | 5.5 | 2.6
Porcelain tile | 4 | 7
Stained / epoxy concrete | 1.6 | 2.4
Walls ($ per sq ft of wall)
Walls | Materials | Labor
Drywall | 0.75 | 2.25
Mold-resistant drywall | 1 | 2.25
Wood / plank paneling | 2.4 | 1.5
Basement wall panel system | 4.2 | 1.4
Ceiling ($ per sq ft of floor)
Ceiling | Materials | Labor
Drywall | 0.8 | 2.2
Drop / suspended | 2.2 | 1.6
Exposed, spray-painted | 0.4 | 0.9
Coffered / tray | 5 | 9
Wall insulation ($ per sq ft of exterior wall)
Insulation | Materials | Labor
Fiberglass batts | 0.9 | 0.8
Rigid foam board | 1.6 | 1.2
Closed-cell spray foam | 2.3 | 1.4
None | 0 | 0
Bathroom (each)
Bathroom | Materials | Labor
None | 0 | 0
Half bath | 3500 | 5000
Full bath | 6500 | 8500
Upscale full bath | 12000 | 12000
Plumbing rough-in if the slab must be cut: $800 materials + $3,500 labor. DIY trades add a $150 tool-rental allowance and remove that trade's labor.
Budget categories (used by the Quotes and Expenses dropdowns)
Prep, cleanup & dumpster
Framing & doors
Insulation
Walls
Ceiling
Electrical & lighting
Bathroom
Flooring
Paint & finishing
Trim & baseboard
HVAC extension
Insulated subfloor
Interior waterproofing
Egress window
Wet bar
Media room prewire
Soundproofed ceiling
Permits & inspections
Radon mitigation
Stairs & railings
Furniture & decor
Other
Contingency
Trades
Prep & demo
Framing
Insulation
Electrical
Plumbing
Drywall & ceiling
Flooring
Painting
Trim & doors